AfriReVision

Phase 6 — Development Roadmap

MVP, releases, sprints, milestones and timelines

Enterprise Reinsurance Management Platform — July 2026

Team assumption: 2–3 engineers + this AI pair. Sprint = 2 weeks.

## 1. MVP Scope (Release 1, "Production Foundation") — Sprints 1–7 (~14 weeks)

Everything in PRD Must-Have: engine tests, backend (identity, entities, finance, audit), server-enforced module access, migration from localStorage, maker-checker, period close, XLSX, backups, monitoring, deploy.

## 2. Phase 2 Scope (Release 2, "Financial Depth") — Sprints 8–11 (~8 weeks)

FX service + consolidation, notifications, report archive, yield-curve discounting, per-risk sum-insured profiles (real surplus/exposure rating), performance hardening, TOTP for admins.

## 3. Phase 3 Scope (Release 3, "Reach & Intelligence") — Sprints 12–15 (~8 weeks)

Cedant/broker portal (read-only statements, bordereaux upload), real ML models per model registry, configurable risk appetite, localisation, multi-entity groundwork.

## Sprint Plan (Release 1)

| Sprint | Goal | Key deliverables |
| --- | --- | --- |
| S1 | Trust the maths | Vitest harness; golden tests: actuarial, IFRS 17, accounting, retro, pricing engines; CI pipeline (lint fix, typecheck, tests) |
| S2 | Identity | Fastify skeleton, users/user_modules schema, Argon2id, JWT+refresh, admin API; frontend auth wired to API |
| S3 | Core entities | Treaties/claims/underwriting/premium APIs + repositories; src/api/ data layer behind DataStore actions |
| S4 | Migration & audit | localStorage→DB migration tool with validation report; server audit service; RLS policies |
| S5 | Finance backbone | Accounting APIs, manual journals, maker-checker workflow + approvals inbox UI |
| S6 | Close & files | Period close service + IFRS 17 opening balances; XLSX export/import; PDF reports |
| S7 | Production readiness | Staging+prod environments, backups+restore drill, monitoring/alerts, security scan pass, UAT, go-live |

## Release Plan & Milestones

- M1 (end S1): All engines under test — green baseline.

- M2 (end S2): First real login against the backend.

- M3 (end S4): Company data lives in Postgres; audit immutable. (Point of no return — localStorage becomes cache only.)

- M4 (end S6): First period closed in-system.

- M5 (end S7): Production go-live. → UAT sign-off gate with CUO + Finance Manager + Actuary.

- M6 (end S11): Release 2 live (multi-currency close).

- M7 (end S15): Portal live.

## Dependencies

- S3 depends on S2 (auth) and S1 (tests protect refactors).

- Migration (S4) blocks maker-checker/close (S5–S6) — they need server data.

- Period close depends on accounting APIs; IFRS opening balances depend on close.

- Restore drill (S7) depends on backups configured (S6→S7).

- Regulator data-residency confirmation needed before S7 hosting commit (start inquiry in S1).

## Estimated Timeline

| Release | Duration | Calendar (from kickoff) |
| --- | --- | --- |
| R1 Production Foundation | 14 weeks | Months 1–3.5 |
| R2 Financial Depth | 8 weeks | Months 3.5–5.5 |
| R3 Reach & Intelligence | 8 weeks | Months 5.5–7.5 |

Buffer policy: each release carries one unplanned sprint of slack before the next begins; UAT defects burn the buffer, not the scope.